## Action Plan Input (hidden)
Tasks
Start | End | Duration in Days | Label
2019-08-28 | 2019-11-08 | 72 | Draft Action Plan
2019-09-03 | 2019-10-07 | 34 | Meet with Partners/Develop Risk Assessment
2019-10-08 | 2019-11-07 | 30 | Compile Input from Risk Assessment and Partner Meetings
2019-11-12 | 2019-11-25 | 13 | ODR/DEO Review 1
2019-11-25 | 2020-01-10 | 46 | Public Comment Period
2020-02-03 | 2020-04-03 | 60 | HUD Reviews
Milestones
|  | Date | Label
|  | 2019-08-28 | Mitigation Register Applicability Date (08/28/19)
|  | 2019-11-08 | Action Plan Draft Due for Review (11/08/19)
|  | 2020-02-03 | Action Plan Due (02/03/20)
|  | 2020-04-03 | HUD Review Due (04/03/20)

## GIP Michael
General Infrastructure Program Implementation Plan Timeline |  |  | Public Notice Dates:
Start Date:
Entity: |  |  | End Date:
Primary Contact:
Date: | mm/dd/yyyy
Deliverables and Tasks
Activity | Start | End | Duration | Label
Project Start
Task 1 | 2020-02-03 | 2020-03-03 | 29 | Environmental Review
Task 2 | 2020-03-03 | 2020-04-03 | 31 | Engineering Design
Task 3 | 2020-04-04 | 2020-05-04 | 61 | Site Development
Construction 50% Complete
Task 1 | 2020-05-06 | 2020-07-06 | 61 | Construction Phase I
Task 2 | 2020-07-08 | 2020-08-08 | 31 | Construction Phase II
Task 3 | 2020-05-06 | 2020-07-06 | 61 | Construction Phase III
Close Out
Task 1 | 2020-07-08 | 2020-08-08 | 31 | Inspections
Task 2 | 2020-08-20 | 2020-09-01 | 12 | Project Closeout
Task 3 | 2020-09-01 | 2020-12-25 | 115 | Maintenance and Monitoring